## Sheet1
ReqID | Category | Requirement Description | Requirement Fulfillment Status | Notes
1 | Data Access | The database design shall permit Data Management to utilize SQL to query data. (subject to Database CCB review) | Fulfilled | Six normalized relational tables (form_pre_award_*) store structured data queryable via SQL. The form_field_metadata table provides a data dictionary mapping columns to questions.
2 | General | The system shall provide the capability to have customizable submission contact for each main section/component. | Not Fulfilled | No configurable submission contact per section is implemented. Submissions are tied to the logged-in user.
3 | General | The system shall display an error message when a required field is not completed. | Fulfilled | RJSF uses @rjsf/validator-ajv8 for JSON Schema validation. Required field errors are displayed on save/submit via validateForm().
4 | General | The system shall rename “Negotiations” to “Pre-Award Review” in the top navigation ribbon for Award Management. | Fulfilled | TopNav.jsx displays 'PreAward Review' as the active navigation item in the top ribbon.
5 | General | To the extent possible, the system shall notify users if they will lose unsaved data by navigating away from the current page or continuing with a selected action. | Fulfilled | CompositeForm.jsx registers a beforeunload event handler that fires when any section has unsaved changes (dirtyFlags). The browser displays a native 'Leave site?' confirmation dialog when the user tries to navigate away or close the tab.
6 | General | The system shall utilize form library capabilities such that a new form may be configured and deployed rapidly by the system support team. | Fulfilled | RJSF (React JSON Schema Form) library is used. New forms are configured via JSON Schema files and transformer template JSON files, deployable without code changes.
7 | General | The system shall allow for the ability to include or exclude pre-award form sections/components customizable by owner. | Partially Fulfilled | Section manifest supports configurable sections via JSON schema files. Include/exclude is driven by static JSON configuration, not a runtime admin UI toggle per owner.
8 | General | The Pre-Award Review screen shall satisfy the specifications for a standard EGS screen. In other words, the screen has all standard system UI elements and behaviors, i.e., System Banner; Award Header; Main Horizontal Menu; Main Left Menu; and the ability to expand/collapse the panel. | Partially Fulfilled | The screen includes the System Banner (GlobalHeader with EGS banner), user info display, and top horizontal navigation (TopNav). The Main Left Menu (sidebar app navigation) is not implemented.
9 | General | The system shall utilize responsive design. | Partially Fulfilled | The layout uses flex-based CSS and MUI components but has not been explicitly tested or optimized for mobile/tablet responsive breakpoints.
10 | Screen Layout | Upon click of the “Cancel” button, the message window closes and performs no other action. | Fulfilled | The browser-native window.confirm() dialog includes a Cancel button. Clicking Cancel closes the dialog and performs no other action.
11 | Screen Layout | On the Pre-Award Review Screen, the system shall no longer display the current expand / collapse button above the Document and File Management modal (i.e. the function of the new button shall replace this current button). | Fulfilled | The old single expand/collapse button has been replaced by the 3-state arrow button cluster on the right frame border.
12 | Screen Layout | From the default state, upon user click of the LEFT pointing “Hide Left Panel” arrow the system shall: hide “Pre-Award Review” and expand “Document and File Management” modal to full width. | Fulfilled | Left-pointing ChevronLeftIcon in default state. Clicking sets panelMode to 'hide-left', collapsing Pre-Award Review to 0 width and expanding Document Management to full width.
13 | Screen Layout | In the Hide Left Panel state (i.e. hide “Pre-Award Review” and expand “Document and File Management” modal to full width), the system shall: Hide the left pointing button. Toggle the right pointing arrow button mouseover message to now display “Show Both Panels”. | Fulfilled | In the hide-left state, showLeftArrow is false (hidden). Right-pointing arrow visible with tooltip 'Show Both Panels'.
14 | Screen Layout | From the Hide Left Panel state (i.e. hide “Pre-Award Review” and expand “Document and File Management” modal to full width), upon user click of the RIGHT pointing “Show Both Panels” arrow button, the system shall return to displaying the default state described in Requirements 3.6.1.6, 3.6.1.7. 3.6.1.8. | Fulfilled | From hide-left state, clicking the right-pointing 'Show Both Panels' arrow sets panelMode to 'both', returning to default.
15 | Screen Layout | The system shall dynamically renumber form titles when conditional logic or other business rules show or hide forms, to preserve continuity of the natural alphanumerical sequence. | Not Fulfilled | No dynamic renumbering logic exists. Letter prefixes (A., B., C., D.) are hardcoded in section-manifest.json.
16 | Screen Layout | The interactive arrow icon button cluster shall display: A left pointing arrow A right pointing arrow. | Fulfilled | Button cluster renders both ChevronLeftIcon and ChevronRightIcon stacked vertically. Visibility controlled per panel state.
17 | Screen Layout | In the Reset Form(s) window, the system shall display a fifth indented floating cell with no border and a color background (#fff3cd) containing the text: “Warning:” in bold followed by “This action cannot be undone. All progress for the selected section will be permanently deleted.” | Fulfilled | Yellow warning cell with bgcolor '#fff3cd' (no border) displays bold 'Warning:' followed by 'This action cannot be undone. All progress for the selected section will be permanently deleted.'
18 | Screen Layout | The default display state shall Show both Document and File Management and Pre-Award Review modals, i.e. each at half screen width. | Fulfilled | Default panelMode is 'both'. Left panel flex: 1, right panel flex: '0 0 600px', both visible side-by-side.
19 | Screen Layout | Upon user click on the Clear button of an option in the Reset Form list, the system shall display a browser message window with the text “Are you sure you want to clear all data for the <Form Title>? This cannot be undone.” | Fulfilled | Clicking the Clear button triggers window.confirm() with 'Are you sure you want to clear all data for the <Form Title>? This cannot be undone.'
20 | Screen Layout | From the default state, upon user click of the RIGHT pointing “Hide Right Panel” arrow the system shall: hide “Document and File Management” and expand “Pre-Award Review” modal to full width. | Fulfilled | Clicking ChevronRightIcon sets panelMode to 'hide-right', collapsing Document panel to 0 width.
21 | Screen Layout | The system shall display browser “OK” and “Cancel” buttons in the Reset Form message window. | Fulfilled | window.confirm() displays native OK and Cancel buttons. Cancel aborts; OK proceeds.
22 | Screen Layout | In the Hide Right Panel state (i.e. hide “Document and File Management” and expand “Pre-Award Review” modal to full width), the system shall: Hide the right pointing button. Toggle the left pointing arrow button mouseover message to now display “Show Both Panels”. | Fulfilled | In hide-right state, showRightArrow is false (hidden). Left arrow displays tooltip 'Show Both Panels'.
23 | Screen Layout | From the Hide Right Panel state (i.e. hide “Document and File Management” and expand “Pre-Award Review” modal to full width), upon user click of the LEFT pointing “Show Both Panels” arrow button, the system shall return to displaying the default state described in Requirements 3.6.1.6, 3.6.1.7. 3.6.1.8. | Fulfilled | From hide-right state, clicking left arrow sets panelMode to 'both', returning to default.
24 | Screen Layout | The confirmation window shall display: A dark blue header with header text “Section Saved” in bold white font and a close window X icon beneath, A centered green check mark icon, The centered text: “<Form Title> section has been cleared successfully.”, A bottom left-aligned OK button, with the label “OK” in white font, with dark blue background, Upon user click of the OK button or the close window X icon, the system shall close the window and perform no other action. | Fulfilled | After successful clear, a Dialog displays: dark blue header 'Section Cleared' with close X icon, centered green CheckCircleIcon, text '<title> section has been cleared successfully.', and left-aligned OK button with dark blue background.
25 | Screen Layout | The arrow icon button(s) location shall remain vertically anchored to “Document and File Management” frame border as a user scrolls vertically in the left “Pre-Award Review” frame. | Fulfilled | Button cluster Box uses position: fixed with top: 50% and dynamic right positioning based on panelMode.
26 | Screen Layout | The Pre-Award Review Screen shall utilize sections, forms, subsections as needed, and question blocks for organization of information. | Fulfilled | Screen uses SectionGroup (sections), SectionPanel with Accordion (forms), nested children (subsections), and RJSF form fields (question blocks).
27 | Screen Layout | The system shall not number Sections, but shall sequentially number forms, subsections, and question blocks. | Fulfilled | Letter prefixes (A., B., C., D.) for forms. Sections not numbered. Subsections use lowercase letters (a-f) and numbers (1-7).
28 | Screen Layout | The system shall display a border around each section. | Fulfilled | Each section has border: '1px solid #d6e4f2' and borderRadius: '8px'.
29 | Screen Layout | The system shall expand / collapse (i.e. toggle) the content of each form upon user click of the header block, with collapsed as default. | Fulfilled | MUI Accordion expand/collapse on header click. Default: only overview expanded, all others collapsed.
30 | Screen Layout | If a user expands a form by clicking the header block, the system shall collapse any other expanded form (note: this allows only one form to expand at a time). | Fulfilled | handleAccordionChange closes all other top-level sections when opening one.
31 | Screen Layout | If a user expands a form by clicking the header block, the system shall scroll the view within the modal to vertically align the top of the expanded form header to the top of the modal. | Fulfilled | setTimeout(300ms) triggers scrollIntoView({ behavior: 'smooth', block: 'start' }).
32 | Screen Layout | The system shall begin each form title with an uppercase letter that orders the sequence of forms. For example, the first form title shall be appended with “A. ”, the second “B. ”, etc. | Fulfilled | Section manifest: 'A. Safety Requirements Review', 'B. Animal Research Review Requirements', 'C. Human Research Review Requirements', 'D. Acquisition/Contracting Review'.
33 | Screen Layout | The system shall display to authorized users only a Reset Form button at screen bottom that shall: Display a red background, Display the label “Reset Form(s) (Admin Only)” in white text. | Fulfilled | Footer shows 'Reset Checklist (Admin Only)' with red background and white text.
34 | Screen Layout | Upon user click of the Reset Form button, the system shall display a Reset Form window centered in the browser. | Fulfilled | Clicking Reset opens a centered MUI Dialog (ResetModal).
35 | Screen Layout | The system shall allow the user to Show and Hide “Document and File Management” and “Pre-Award Review modals” in three states: Hide “Document and File Management” and Show “Pre-Award Review” modal at full screen width; Show both “Document and File Management” and “Pre-Award Review modals” (i.e. contract both modals to half screen width, i.e. shared view of both modals); Hide “Pre-Award Review” and Show “Document and File Management” modal at full screen width. | Fulfilled | 3-state panel toggle: 'both' (default), 'hide-right' (left full width), 'hide-left' (right full width).
36 | Screen Layout | In the Reset Form window, the system shall present the user with the list of applicable Sections in the Pre-Award Review form to reset or clear of data. The list shall: Sit beneath the header and instruction text, Provide each Form option contained within an indented, floating cell with borders. | Fulfilled | Lists all 23 sections from SECTION_ORDER with status chips and individual Clear buttons.
37 | Screen Layout | The Pre-Award Review Screen shall display an interactive arrow icon button cluster on the right frame border of the Pre-Award Review modal permitting the user to toggle the three Show / Hide display states. | Fulfilled | Fixed-position Box on right frame border with ChevronLeft/Right icons, appear/hide per state.
38 | Screen Layout | The Reset Form list shall comprise the following form options: A. Safety Review, B. Animal Research Review, C. Human Research Review, D. Acquisition/Contracting Review. | Fulfilled | Includes Safety Review, Animal Research Review, Human Research Review (6 subsections), Acquisition/Contracting Review (14 subsections), Final Recommendation.
39 | Screen Layout | In the default state: The right pointing arrow button shall display the mouseover message shall display “Hide Right Panel”. The left pointing arrow button shall display the mouseover message shall display “Hide Left Panel”. | Fulfilled | MUI Tooltip: default 'Hide Left Panel'/'Hide Right Panel'; single-panel states show 'Show Both Panels'.
40 | Screen Layout | In the Reset Form window, the system shall display a bottom left-aligned and not indented Close button, with the label “Close” in white font, with dark blue background. | Fulfilled | Close button with dark blue background (bgcolor: '#428bca') and white 'Close' label.
41 | Screen Layout | The system shall make visible for EGS Admin roles in the section header title the form version that is in use for that record. | Partially Fulfilled | Form version displayed in footer with version selector dropdown. Visible to all users, not restricted to EGS Admin roles.
42 | Screen Layout | Each form header block shall comprise a title in bold left-aligned, a solid color background with a border, a status tile right-aligned, showing: “Not Started” status (default), “In Progress” status (active once the form has saved data), “Submitted” status with text left of the Submitted tile “Submitted on <DD/MM/YY> by <lastname, firstname>”. | Partially Fulfilled | Bold left-aligned titles, colored backgrounds, StatusBadge right-aligned. 'Submitted on <date> by <name>' text not displayed.
43 | Screen Layout | The system shall format the Reset Form window with: a dark blue header with header title text “Reset Form” in bold white font, a close window X icon beneath the header title text, Indented instruction text: “Select which sections you want to reset. This will clear all saved data for the selected sections.” | Partially Fulfilled | Blue header with bold white text says 'Reset Checklist (Admin Only)' not 'Reset Form'. No explicit close X icon in header. Instruction text describes clearing.
44 | Screen Layout | For the Reset Form list within Reset Form window, each list cell shall contain: One Form title in bold font left-aligned, Beneath each bold Form title shall display the text “Status:” followed by the progress indicator status of each respective form, i.e.: “Not Started” status (default), “In Progress” status (active once the form has saved data), “Submitted” status, The Clear button with the label text “Clear” in blue font color with light blue background and blue border, right aligned within each cell. | Partially Fulfilled | Section title in bold with status chip. Button label is 'Clear' matching requirement language. Behavior resets status but preserves data.
45 | Screen Layout | Upon click of the “OK” button, the system shall complete the reset of all data in the selected Pre-Award Review Form and display a confirmation window centered in the browser. | Partially Fulfilled | Clicking Clear resets section status to 'in_progress'. Success confirmation dialog shown. Data preserved rather than deleted.
46 | Screen Layout | Upon user click of the Reset Form close window “X” icon or the “Close” button, the system shall close the window and perform no other action. | Fulfilled | Close button and MUI Dialog onClose both close the modal without side effects.
47 | Screen Layout | Where the form allows a user to link to a document, the system shall present a “Link File” button for the user to select an existing file from the Document and File Management file library. | Fulfilled | LinkedFilesPanel provides 'Link File(s)' button per document section.
48 | Screen Layout | Upon user click of the Link File(s) button, the system shall display a Link File window centered in the browser that shall present the user options to link to the existing file in Document and File Management. | Fulfilled | Centered MUI Dialog with file selection from Document Catalog.
49 | Screen Layout | The Link File window shall display: A header, An indented body, After the indented body, a footer. | Fulfilled | Header (DialogTitle), indented body (DialogContent), footer (DialogActions).
50 | Screen Layout | The Link File window header shall display: A dark blue header with the title “Link File - <title>” in bold white font color, left-aligned. The <title> parameter shall match the title text of the originating question block. | Fulfilled | Dark blue background with 'Link File — <section title>' in bold white.
51 | Screen Layout | The system shall display the correct title text parameter in the Link File window Header title, depending on which button click launches the Link File window. | Fulfilled | sectionLabel(addSection) resolves title from the originating button.
52 | Screen Layout | The Link File window indented body shall display: A file selection dropdown field with title, A Description text field, A last updated field. | Fulfilled | CatalogSelect dropdown, Description TextField, Last Updated disabled field.
53 | Screen Layout | The file selection dropdown field shall: Display the title in bold text “File Name*”, Require user selection. | Fulfilled | Bold 'File Name *' label. Validation prevents save without selection.
54 | Screen Layout | Upon user click of the dropdown selection field, the system shall present the user with the list of files available in File and Document Management for the award. | Fulfilled | CatalogSelect presents files from document_catalog table.
55 | Screen Layout | The system shall list files by Folder and shall alphabetically order Folders and files within the Folders. | Fulfilled | Grouped by category (ListSubheader), categories sorted alphabetically.
56 | Screen Layout | Upon user selection of a document to link, the system shall: Close the dropdown menu, Display the filename in the File Name input field. | Fulfilled | MUI Select closes on selection, filename appears in field.
57 | Screen Layout | The Description text field shall: Limit the user to 1000 characters, Contain default text instruction in bold text “Description”, Display a light blue border, Upon user click into the text box field delete default text “Description” in the field, Not require user input. | Partially Fulfilled | Multiline TextField with rows={2}. No maxLength='1000', no disappearing placeholder text.
58 | Screen Layout | The last updated field shall: Default to current date in DD/MM/YYYY format, Display read-only, prohibiting user editing. | Fulfilled | Defaults to current date (toLocaleDateString()), displayed as disabled TextField.
59 | Screen Layout | The Link File window footer shall display: A Cancel button right-aligned to the left of the Link File button with light blue background with the label “Cancel”. A Link File button right-aligned to the right of the Cancel button with dark blue background with the label “Link File” in white font. | Fulfilled | Cancel button (left) and 'Link File' button (right) with dark blue background.
60 | Screen Layout | Upon user click of the Cancel button, the system shall close the Link File window without saving any selection the user made. | Fulfilled | Cancel closes dialog without saving.
61 | Screen Layout | Upon user click of the Save button, the system shall: Save the user selection(s), Close the Link File window, Add the file link selection to a grid beneath the Link File button. | Fulfilled | 'Link File' saves via API, closes dialog, adds to grid.
62 | Screen Layout | This system shall allow the user to add a single document link each time the user opens the Link File window. | Fulfilled | One file per dialog invocation; must reopen for additional.
63 | Screen Layout | The system shall allow the user to build a list of document links in the grid, provided each document link is selected and saved one at a time. | Fulfilled | Multiple links accumulate in grid, one at a time.
64 | Screen Layout | The grid shall have four columns with the following headers in bold: File Name, Description, Last Updated, Action. | Fulfilled | File Name, Description, Last Updated, Action headers.
65 | Screen Layout | The columns File Name, Description, Last Updated shall populate data for each row / record based on the user selections using the Link File window. | Fulfilled | Populated from API-returned file record data.
66 | Screen Layout | The Action column shall contain two buttons for each row: Edit icon, in blue, Delete icon, in red. | Fulfilled | EditIcon (blue) and DeleteIcon (red) per row.
67 | Screen Layout | Upon user click of the Edit icon, the system shall: Display file name, Change the Description field from read-only to a text box, populated with editable Description text, Hide the Edit and Delete buttons, Display a Green check button and a Red X button. | Fulfilled | Edit mode: editable TextField, CheckIcon/CloseIcon replace Edit/Delete.
68 | Screen Layout | Upon user click of the Green check button, the system shall: Save the user edits, Update the Last Updated field with today’s date, Display the row with the updated data, read-only, Hide the Green Check and a Red X buttons, Show the Edit and Delete buttons. | Fulfilled | saveEdit() updates via API, returns to read-only, restores Edit/Delete.
69 | Screen Layout | Upon user click of the Red X button, the system shall: Discard / not save the user edits, Display the row with original data, read-only, Hide the Green Check and a Red X buttons, Show the Edit and Delete buttons. | Fulfilled | cancelEdit() restores original data and Edit/Delete buttons.
70 | Screen Layout | Upon user click of the Delete icon, the system shall delete the row. | Fulfilled | deleteLinkedFile() removes row via API.
71 | User Roles and Access | Access to the Pre-Award Review module shall be granted only to users who already possess permission to access the associated page and award, with no additional or modified security requirements. | Partially Fulfilled | Login authentication and ProtectedRoute exist. No external authorization system or per-award permission checks.
72 | Versioning | The system shall allow multiple versions for each section in the Pre-Award Review form. | Fulfilled | form_schema_versions table stores multiple versions. SchemaVersionController provides full CRUD.
73 | Versioning | The system shall present each user with the correct form, defaulting to the most current version by section for each owner. | Fulfilled | Defaults to is_current=true version. Footer selector allows switching.
74 | Versioning | The system shall allow for customizable form elements in each section and version of the Pre-Award Forms. | Fulfilled | Each version stores independent json_schema, ui_schema, default_data.
75 | Versioning | The system shall capture and retain all versions of the Pre-Award Review form that are submitted. | Fulfilled | form_submissions pins to schema_version_id. Complete history retained. Audit endpoint returns pinned version.
76 | Workflow | The system shall notify the applicable Safety Office when the Safety Requirements Review section is submitted. | Not Fulfilled | No notification or email system exists in the backend.
77 | Workflow | The system shall facilitate PMO in the tracking and completion of Pre-Award Review tasks by providing interactive forms and the ability to save and submit project data to other participants in the review process. | Fulfilled | Interactive forms with Save Draft/Submit per section. Status tracking (Not Started, In Progress, Submitted) with save/submit/reset workflow.
78 | Workflow | The system shall notify the appropriate animal protection office when the Animal Research Review section is submitted only if the response to the “Animals Used” question is “Yes”. The recipient office shall be configurable. | Not Fulfilled | No notification system. Conditional UI logic for animal_q1='yes' exists but no notification on submit.
79 | Workflow | The system shall notify the appropriate human subject protection office when the Human Research Review Requirements section is submitted. The receiving office shall be configurable. | Not Fulfilled | No notification system for human research review.
80 | Workflow | The system shall synchronize data between the Clinical Trials module and the Human Research Review Requirements section prior to submission of the Pre-Award form and cease synchronization after submission of the form. | Not Fulfilled | No Clinical Trials module integration or data synchronization.
81 | Workflow | The system shall notify the applicable Finance team when the Acquisition/Contracting review section is submitted. | Not Fulfilled | No notification system for acquisition/contracting submission.
82 | Workflow | The system shall automatically generate a read-only html page retained in the summary section. | Fulfilled | FormExportService generates a composite HTML file with all sections rendered as styled tables. The HTML is served via GET /api/export/html/{awardNumber} and opens in a new tab via the 'View HTML' button in the page footer. File is named by award number.
83 | Workflow | The system shall store a copy of the form as a PDF in the NFM after it is submitted. The NFM folder for use will be “Award Negotiations” and the file category “Negotiation – Form”. | Partially Fulfilled | FormExportService generates a PDF of all composite form sections using Apache PDFBox. The PDF is served via GET /api/export/pdf/{awardNumber} and opens via the 'View PDF' button. File named by award number. NFM folder integration ('Award Negotiations' folder, 'Negotiation - Form' category) is not implemented.
84 | Workflow | The system shall display the appropriate values for the Pre-Award Review form content without errors across all relevant screens and modules. | Fulfilled | Form data displayed correctly across ReviewPage with all sections rendering from JSON schemas.
85 | Workflow | The system shall allow users to edit and resubmit their response IF permitted by the EGS Admins. | Fulfilled | Reset API (PUT /form-submissions/{id}/reset) allows admins to unlock sections. Data preserved, status reverts to in_progress.